#### Annex 8

#### Indicative 2007-2013 NDP  Time Table

|  | 2003 |  |  |  | 2004 |  |  |  | 2005 |  |  |  | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 |
| Management and Co- ordination Structures |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsibilities and Competences Guidance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Clarify outputs and relationship with EC |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobilisation of socio-economic actors |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NDP and OP Development Guidance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft Strategic Goals and Priorities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft Ops 1stdraft / 2nd draft |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicative and detailed budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ex-Ante Evaluation Undertaken |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Draft NDP |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Absorption Capacity Assessed |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approval and Submission to EC |  |  |  |  |  |  |  |  |  |  |  |  |  |