DONOR AGREEMENT ANNEX 1

Country: BULGARIA Ministry of Health 5, Sveta Nedelia Sq., Sofia Implementing institution: Ministry of Health “Health Prophylaxis and State Sanitary Control” Directorate 39, Stamboliyski Blvd., Sofia

Title of Project: “Strengthening Food Safety and Nutrition Services in SEE: Component One: Food Policy and Legislation” Decision on Component One of 7th Meeting of SEE Health Network, Tirana, Albania, November 2003 and signed by the nominated representatives the eight SEE beneficieries countries, specified below, Greece, Council of Europe and WHO Regional Office for Europe at the 7th Meeting of the Stability Pact Initiative for Social Cohesion, Brussels, Belgium, 8 December 2003.

Justification: Food safety and the surveillance and control of food borne and diet related diseses is a state responsibility in the SEE countries and was well functioning for decades, but since the countries are in transition to market economy this systems has to be adapted to the modern preventive approach concept. The SEE countries have enormous food trade potential and, also, they have potential for further development of their agricultural, food processing and tourism sectors, in addition to improving public health.

Project Objective: To strengthen the institutional capacity of the public and private components of the health system to achieve the objectives of decreasing the food-borne and diet related diseases through control and prevention at central, regional and local levels with an inter-country and intersectoral approach.

Project outcomes (deliverables) : Through regional ( inter-country) and national activities each SEE will achieve the following: - Assessment of food and nutrition status of the country (country profile) - Development of National Food and Nutrition Policy and Action Plan (new or revised) - Draft Food Safety Strategy - Drafts of Food Laws or revision of existing ones - Participation in a regional network - Enhanced national capacities in the area of food safety - Raising awareness of food and nutrition as an important value of the community with major social and economic implications The above outcomes of the Project will contribute toward: - Improving food safety and nutrition of the countries' population - Support the development of the agricultural, food processing, trade and tourism sectors, and - Promoting social cohesion, reconciliation and stability within the region

Geographical focus: South Eastern Europe (SEE) Country(ies): Albania Bosnia and Herzegovina Bulgaria Croatia Republic of Moldova Romania Serbia and Montenegro, and The Former Yugoslav Republic of Macedonia

Project Implementation Dates: Starting Date: 01 November 2004 Completion Date: 01 November 2005

Budget: The total budget for the component one is € 356.684 provided by the following donors: Greece:; 150.000 Euro. Italy:; 105.000 Euro. Switzerland:; 43.000 Euro. WHO:; 58.684 Euro. The total amount of € 356.684 is shared equally by the eight beneficiary countries. The budget for Component One for each country is € 44.585 Euros. Out of this amount € 21.428 will be disbursed directly to the country to be used for the in-country (national) activities and the rest of € 23.157 will be used for the inter-countries activities under the coordination of the Regional Project Office. Bulgaria will recieve the amount of € 21,428 for in-country activities from : Greece : € 21,428

SOCIAL COHESION INITIATIVE

SOUTH EASTERN EUROPE HEALTH NETWORK

“Health Development Action for south-eastern Europe”

____________________________________________________________________________

Strengthening Food Safety and Nutrition Services

in South East Europe

Project Component One:

Food Policy and Legislation

Decision

Signed:

By the Senior Government Health Officials from South-eastern Europe

At the Seventh Meeting of the Stability Pact Initiative for Social Cohesion Working Group,

Brussels, Belgium, 08 December 2003

We, the National Health Coordinators from the South East European countries  (SEE), nominated by the Ministers of Health of Albania, Bosnia and Herzegovina, Bulgaria, Croatia, Republic of Moldova, Romania, Serbia and Montenegro and the Former Yugoslav Republic of Macedonia (thereafter called the “representatives”), at our 6th Meeting of the SEE Health Network, established in partnership with the Council of Europe and WHO Regional Office for Europe under the framework of the Stability Pact Initiative for Social Cohesion, met in Sarajevo, 30 May – 1st June 2003.  We consider this initiative to be a timely, appropriate, and essential contribution to the promotion of peace and to the guiding principles of the Stability Pact for South East Europe and for the European Union Stabilization and Association process. The Dubrovnik Pledge of the Ministers of Health of South East Europe calls for immediate action and provides solid political commitment for its success. In follow-up to the Dubrovnik decisions we agree to the following:

### DECISION

Of the 6th Meeting of SEE Health Network:

Health Development Action in South East Europe

In reviewing the food safety and nutrition priorities, we, the representatives of eight South East European countries, discussed, on our own initiative and in follow-up to the Dubrovnik Pledge of the Ministers of Health, the ways and means to build concerted political action in the food safety and nutrition field related to the region’s democratisation, stabilization, development, social cohesion, peace and reconciliation.

We consider new food safety and nutrition policies, legislation and services as an appropriate instrument to resolve some of the key priority problems of the vulnerable populations in the region, to influence, from the public health point of view, other areas, through identification of key actors, and to develop concerted actions.

We note that, at present, food safety and nutrition policies reforms in the region need to be re-assessed and updated in the light of the Council of Europe’s conventions and recommendations on health, human rights and ethics, the European Union Article 152 of the Amsterdam Treaty and EU directive on Human Rights, the WHO “Food and Nutrition Policies and Action Plan in the European Region: 2000-2005”and the resolution endorsed by the 52nd WHO Regional Committee for Europe on the recommendations of the WHO/FAO Pan-European Conference for Food Safety and Quality.

We concluded that the food safety and nutrition sector needs to acquire sufficient standing in all government policies, legislation and regulations, as well as in future obligations of the countries to implement Community legislation based on the Article 152 of the Amsterdam Treaty. We believe that a political input of the SEE countries would be beneficial to both the EU Stabilization and Association and the Stability Pact processes, and also, to strengthening public health and food safety and nutrition in the SEE region.

To achieve these objectives, we, the “representatives”:

- Approve the final draft of the project “Strengthening Food Safety And Nutrition Services – Component One: Food Policy and Legislation”(Annex 1) subject to subsequent adjustment in the course of implementation as decided by the Project Steering Committee

- Agree, in the frame of the available resources, to start the implementation of Component One “Food Policy and Legislation”

- Approve the Component One Logical Framework (LFA), Project Implementation Plan (PIP), organizational set-up and budget breakdown (Annexes 2, 3, 4 and 5)

- Commit us and our national technical counterparts to the agreed time frame to facilitate and launch the project implementation as of November 2002.

- Request the Ministers of Health of the seven SEE to endorse the above decisions, to maintain continuous political commitment and support, including by mobilizing domestic human and financial resources, to the project implementation, and, finally, to control and supervise the progress and impact of implementation at national and regional levels.

- Thank the Social Cohesion Initiative of the Stability Pact and the Governments of Greece and Italy, the Council of Europe and WHO Regional Office for Europe for their kind political, technical and financial support to the project.

- Recognize the interest and commitment of the Governments of Hungary and Slovenia to the food safety and nutrition related action in the SEE region.

- Invite FAO to consider within its mandate, eventual support to the implementation of this project, in the framework of the recommendations of the FAO/WHO Pan European Conference on Food Safety and Quality.

- Recognize the interest expressed by the Governments of those countries and institutions, which promoted and attended the FAO/WHO Pan-European Conference on Food Safety and Quality in the  food safety and nutrition related actions in the SEE region, and invite them to consider their eventual support to the project implementation.

We, the “representatives”, highlight that to assess the progress in implementing the Dubrovnik Pledge in all seven areas, and particularly in achieving the objectives in the area of food and nutrition, a consultation of Ministers of Health of the SEE countries towards the end of 2004 would be appropriate. Furthermore, such a ministerial consultation could serve to further strengthen collaboration in the health field between SEE countries, and will bring their experience and lessons learned to the health sectors of other countries both in Europe and globally.

## Annex 1

Strengthening Food Safety & Nutrition Services

in South East Europe:

Albania, Bosnia & Hercegovina, Bulgaria, Croatia, Moldova, Romania, Serbia and Montenegro and the Former Yugoslav Republic of Macedonia

Project Component One:

Food Policy and Legislation

| #### Programme #### Framework | Food and Nutrition Policy and Action Plans Food Legislation and Services |
| --- | --- |
| #### Background and justification #### Objective: #### Project purpose: #### Project Component One description: Project Component two: Description (upon availability of funds) | The surveillance and control of food borne and diet related diseases is a state responsibility in SEE countries and was well functioning for decades, but since these countries are in transition to market economy this system has to be adapted to the modern preventative approach concept . The SEE countries have enormous food trade potential and, also, they have potential for further development of their agricultural sectors. In order to access EU and integrate into the common market it is necessary for these countries to harmonize all legislation and procedures in food safety according to Acquis communautaire and Codex Alimentarius standards. In order to acquire high level of safety of food and protection of health all necessary instruments like legislation and control services have to be revised, updated and food control strategies have to be clearly identified. Also, strengthening of the nutrition advisory services and integration of the nutritional strategy in the overall health policy in SEE countries would reduce burden of nutrition related diseases and thus promote health. The overall aim is to decrease the number of the food-borne and diet related diseases through control and prevention. The specific objective of the project is to improve the speed and quality of detection monitoring, reporting and response to food contamination in SEE countries. The project purpose is to strengthen the institutional capacity of the public and private components of the health system to achieve the objectives stated at central, regional and local levels with an inter-country and intersectoral approach. Regional coordination infrastructure will be established through the creation and operation of a regional network for food safety and nutrition. This network will contribute to following international recommendations, including EU directives, norms, guidelines and methods of data reporting and surveillance. Policy of legislation development and harmonization among SEE countries should be based on standards of the WHO FAO Codex Alimenterius Commission and the EU for food safety and prevention of food borne diseases. Institutions in charge of food control and nutrition advisory services will be reformed organisationally and staff trained in new working procedures, including EU directives, EU Dietary Guidelines and EU Recommended Nutrient Intakes and Codex Alimentarius standards. Laboratories will be equipped to address traditional and emerging food and diet related diseases and facilitate trade. A number of professionals in central, regional and local institutions will be trained in new procedures. |
| #### Component one: Steps: Outputs: Activities: a) At regional level: b) At national level: | - Government commitment - Organisational framework - Implementation - Food legislation analysis and revision - Food and Nutrition Policy and Action Plans - Forum on Food Safety Agencies - Sub-regional Network on Food Safety - Capacity building, planning and management of new investment project proposals 4. Evaluation and fund raising - Food and Nutrition Action Plans analysis - Draft Food Safety Strategies - Drafts of Food Laws or revisions of existing food laws - Concept and institutional framework for modern food safety control - Drafts of new projects in Nutrition - Regional Food Safety network operational - Enhanced capacities for Food Safety (trained officials, institutions, experts - Establishment of the project organisational and managerial set-up - Sub-regional network on Food safety - Database and library of all relevant international and national documents in food safety - Workshop on Food and Nutrition Policies and Action Plans (Brijuni 2002) - Workshop on Nutrition Food Safety policies and legislation (Belgrade 2002) - Pan-European conference on Nutrition with meeting of SEE representatives - Draft of the new project proposal in nutrition, (Athens 2003) - Workshop and training on food legislation, (Belgrade 2003) - International fora for capacity building: Food Safety Agencies - Capacity building for project planning and management - Process and criteria for reporting, monitoring and evaluation - Drafting of Food and Nutrition Action Plans - Establishment of inter-ministerial body (IMB), Task Force and scientific advisory committees, to supervise the implementation of the project. This IMB could be a base for development of the future national food safety agencies and could be related with National Codex Committees. - Designing of Food Safety Strategies and National Action plans for their implementation - Drafting or revision of food laws - Updating or plan for updating of secondary legislation - Development of Codes of Practices on enforcement of legislation - Creation of portfolio of investment project proposals- assessment of needs, creation of projects and Terms of References, additional fund rising - Specific national activities in line with the requests of acquis communautaire will focus primarily on: ALB: Revision of the Food Law and development of codes of practice/guidelines on enforcement of legislation BIH: Development of Food Law and secondary legislation, development of Food Safety Strategy with Action Plans BUL: Revision of the Food Law, reform of the inspection services for HACCP audits, development of Codes of Practice (Guidelines) on enforcement of legislation, CRO: Revision of the draft and endorsement of the Food Law, development of Food Safety Strategy, secondary legislation, Codes of Practices, creation of inter-ministrial co-ordination bodies-Food Safety Authority, FYM: Revision of Food Law Development of Codes of Practice (Guidelines) on enforcement of legislation, creation of the Food Control Strategy MDA: Development of Food Law (Secondary Legislation); Food Safety Strategy. ROM: Development of Codes of Practice (Guidelines) on enforcement of legislation Serbia & Montenegro: Development of a Food Safety Strategy, development of Food Law, revision of the secondary legislation, Codes of Practices, reform of inspection services, Food Safety Agency |
| #### Countries: | Albania, Bulgaria, Bosnia and Herzegovina, Croatia, Republic of Moldova, Romania, Serbia and Montenegro, and the Former Yugoslav Republic of Macedonia |
| #### Donor Countries: | Greece Italy |
| #### Neighbor Countries: | Hungary Slovenia |
| #### Potential External Partners: | Council of Europe Council of Europe Development Bank EU countries and non/EU countries: Sweden, Ireland, United Kingdom EC/SANCO; Food and Veterinary Office, Dublin and Food Safety Production and Distribution Chain, Brussels European Food Safety Authority European Reconstruction Agency FAO |
| #### WHO : #### Responsible programmes WHO offices | WHO/ Food Safety WHO/ Nutrition & Food Security WHO Country Office in the participating SEE countries |

Annex 2

Logical Framework (Matrix)

For the Implementation of the Component One of the SEE Project Food Legislation

November 2002 – July 2004

| #### Steps | Outputs | Activities | Indicators of verifica tion | Means of Verification | Responsible Organi zations | Time frame | ##### Critical assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Inception and organizational set-up (at both regional and country levels) |  |  |  |  |  |  |  |
| 1. Govern ment Commit ment | 1.1 Approval of final project | 1.1.1 Revision and finalization of project 1.1.2 Approval of final draft and annexes by Government representatives 1.1.3 Endorsement of the decision by the Governments 1.1.4 Presentation of the project to donors | Finalized project Attaining and keeping the SEE Governments commitment | Decision of Sarajevo meeting Letters from Ministries Contractual agreements | MoH of SEE WHO COE Donor country | 6 months for activities 1-3 20 months for activity 4 | Disagreement between SEE can delay project start-off |
|  | 1.2 Steering Committee & Executive Committee | 1.2.1 Nomination of country representatives 1.2.2 SC meetings on progress 1.2.3 Nomination of members to the EC | Intercountry composition of SC member | Governments’ decision WHO decision CoE decision | MoH of SEE WHO Donors CoE Project SC | 2 months 6-7 months | Assumes political will and agreement between lead Ministeries. Failure to agree could cause major delay or failure to establish IMC (Health and Agriculture Ministeries not coordinated in most countries). |

| Steps | Outputs | Activities | Indicators of verifica tion | Means of Verification | Responsible Organi zations | Time frame | Critical assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Inception and organizational set-up (at both regional and country levels) |  |  |  |  |  |  |  |
| 1. Government Commitment | 1.3 Inter- ministerial Bodies at country level | 1.3.1 Nomination of a country project coordinator 1.3.2. Establishment of the Interministerial Body (IMB) and coordinator 1.3.2 Approval of Terms of Reference for IMB | Interministerial composition of the IMB members | Government decision | MOH of SEE | 7-8 months |  |
| 2. Organisa- tional Frame work | 2.1 Implementation infrastructure | 2.1.1 Approval of Terms of Reference for RPM and CPMs 2.1.2 Selection and recruitment of Regional Project Manager 2.1.3 Selection and recruitment of CPMs in each country 2.1.4 Establishment of offices 2.1.5 Equipment 2.1.6 Selection of international consultants on food legislation (both from the region and from EU countries) | Qualifications, positions and institutional affiliations of persons involved Consultants selected | Project organization plan ToRs RPM CPMs List of national teams and advisory bodies List of consultants | Project EC MOH of SEE WHO | 6-7 months | Lack of funds or delay of arrival of funds from donor countries to recruit an international project coordinator and consultants |
|  | 2.2 Work plan and time Table | 2.2.1 Preparation of detailed work plan and timetable for project coordination and implementation | Work plan and timetable developed | Coordination and implementation plan Timetable for implementation | RPM CPMs MoH of SEE | 7-8 months |  |

| #### Steps | Outputs | Activities | Indicators of verifica tion | Means of verification | Responsible Organi zations | Time frame | ##### Critical assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3. IMPLEMENTATION / COMPONENT ONE |  |  |  |  |  |  |  |
| A. AT REGIONAL LEVEL: |  |  |  |  |  |  |  |
| 3. Implementation | 3. A.1 Food and Nutrition Policies and Action Plans | 3.A.1.1 Provision of international guidance on the process and content of NFNAPs and policies 3.A.1.2 Continuous assistance and review of SEE countries’ NFNAPc 3.A.1.3 1st Technical Workshop on FNAPs, cardiovascular diseases and nutrition in the SEE region, Brijuni, Croatia, September 2002 3.A.1.4 2nd Technical Workshop on FNAPs, Belgrade, November 2002 3.A.1.5 Pan-European Conference on Nutrition with a satellite meeting of SEE on a new draft project proposal on nutrition, Athens, February 2002 | International guidance collected and provided | Guidance | WHO FAO RPD | Month 5th and beyond |  |
|  |  |  | Assistance, external review and coaching provided |  |  | Continuous |  |
|  |  |  |  |  |  | Month 1 |  |
|  |  |  |  |  |  | Month 3 |  |
|  |  |  |  |  |  | Month 6 |  |
| 3. Implementation | 3.A.2 Food legislation and systems analysis and revision | 3.A.2.1 Elaboration and distribution of questionnaire on Food Legislation 3.A.2.2 Provision of information on the existing food legislative framework in the SEE 3.A.2..3 1st Technical SEE Workshop on Nutrition and Food Safety Legislation: Presentation and discussion of the actual legislative situation in the SEE countries 3.A.2.4 Preparation of detailed Country Reports on the current legislative framework on Food Safety (incl. gathering intersectorial information, analyzing the situation, proposed updates and reforms) | Questionnaire on food legislation distributed and completed Recommendations from the countries Presentation of the information on the food legislative framework | Questionnaire on food legislation Responses of the questionnaire Country reports completed List of necessary legal updates and reforms presented | WHO National Project Coordinators in cooperation with national experts from the Ministries of Health, Agriculture, Trade etc. and other stakeholders | 5 months 7-8 months 3 months 10-12 months | Lack of national support or/and coordination between responsible ministries and stakeholders |

| #### Steps | Outputs | Activities | Indicators of verifica tion | Means of verification | Responsible Organi zations | Time frame | ##### Critical assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| IMPLEMENTATION / COMPONENT ONE |  |  |  |  |  |  |  |
| A. AT REGIONAL LEVEL: |  |  |  |  |  |  |  |
|  | 3.A.3 Food legislation revision | 3.A.3.1 2nd Regional Workshop on Food Policy and Legislation in the SEE; - Provision of the basic principles for the update of the National Food Legislation (primary General Food Law and secondary regulations), - Introduction to the EU legislative framework and to the Codex Alimentarius Standards - Presentation necessary reforms on food legislation in the SEE countries. | Country Project coordinators trained to update of the National Food Legislation | Publication of the report of the workshop including the presentations of the countries and recommendations to governements | International project coordinator and consultants National Project coordinators | Month 9 | Lack of funds to hire an international project coordinator and external consultants Lack of National support |
|  | 3.A.4 Food Control Systems | 3.A.4.1 Organizing a Regional Forum to discuss development of National Food Safety Strategies, including the basis for establishment of national Food Safety Agencies in the light of EU developments | Exchanged experiences and models | Report and recommendations | WHO FAO EC CoE MOH of SEE RPM | Month 18 |  |
|  |  | 3.A.1.2 Regional training on investment projects planning and management |  |  |  | Month 16 |  |
|  | 3.A.5 SEE Regional Food Safety Network | 3.A.5.1 Nomination of responsible national institutions |  |  | SEE MOH National Institutions RPM CPMs WHO FAO | Month 12 |  |
|  |  | 3.A.5.2 Establishing of communication lines through e-mail as a start |  |  |  | Month 12-13 |  |
|  |  | 3.A.5.3 Website |  |  |  | Month 13-14 |  |
|  |  | 3.A.5.4 Database and library |  |  |  | Month 13-20 |  |

| #### Steps | Outputs | Activities | Indicators of verifica tion | Means of verification | Responsible Organi zations | Time frame | ##### Critical assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3. B. AT NATIONAL LEVEL |  |  |  |  |  |  |  |
| 3. B Implementation | 3.B.1 National Food and Nutrition Action Plan | 3.B.1.1 Establishing national Task Force 3.B.1.2 First draft NFNAP 3.B.1.3 International review 3.B.1.4 Second draft NFNAP 3.B.1.5 Governmental and public consultations 3.B.1.6 Finalization of NFNAPs 3.B.1.7 Adoption |  |  |  | Month 9 Month 20 |  |
|  | 3.B.2 Food Legislation update | 3.B.2.1 Drafting and/or revision of the primary Food Law 3.B.2.2 Formulating of National Food Safety Strategy and framework for the development of secondary regulations 3.B.2.3 Development of codes of practice on the enforcement of the food law 3.B.2.4 Particular technical support tailored to countries needs aiming at the reorganization and strengthening of the food control systems for the implementation of food legislation, Creation of inter-ministerial co-ordination bodies/agencies, etc) | Preparation of the draft of the General Primary Food Laws | Inter-ministerial commission Presents the final draft of the General Food Law | Inter-ministerial commission and National Project coordinators International project coordinator External consultants | Month 9 Months 20 | Lack of funds for international project coordinator and external consultants Lack of commitment at national level Difficulty in recruiting appropriate consultants within budget |
|  | 3.B.3 Food Control System Concept | 3.B.3.1 Situation Analysis |  |  |  | 10-11months |  |
|  |  | 3.B.3.2 Analysis of international recommendations and models, particularly in the light of EU developments |  |  |  | 11-12 months |  |
|  |  | 3.B.3.3 First draft concept on a national food control system |  |  |  | 14-15 months |  |
|  |  | 3.B.3.4 Public discussion |  |  |  | 16-18 months |  |
|  |  | 3.B.3.5 Investment project proposals |  |  |  | 16-18 months |  |

| #### Steps | Outputs | Activities | Indicators of verifica tion | Means of verification | Responsible Organi zations | Time frame | ##### Critical assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3. B Implementation | 3.B.4 Capacity building and coaching for implementation | 3.B.4.1 National workshops tailored to the needs of the individual countries 3.B.4.2 Provision of international expert consultations upon request | Recommendations from the countries | Report form the meeting with recommendations for a code of practice | WHO International project coordinator External consultants National Project coordinators | Months 11 and beyond | Lack of funds for international project coordinator and external consultants |
| C. EVALUATION ( At both regional and national levels) |  |  |  |  |  |  |  |
| 4. Evaluation and Fund raising for follow up | 4.1 Evaluation of the Implementation | 4.1.1 Preparation of system and criteria for project reporting, monitoring and evaluation 4.1.2 Progress and completion report 4.1.3 Evaluation of the update of the primary food laws and of the national situation for development of secondary specific food regulations 4.1.4 Additional fundraising for capacity building to implement food legislation (surveillance and monitoring, training for inspectors and food producers, training for professionals from laboratories for food control, analytical quality assurance programmes, etc.) | Reports from the countries Conclusions Recommendations | National and sub-regional evaluation reports Fund raising Proposals finalized | CPMs RPM External consultants WHO, CoE MoH of SEE Donors | Months 9-12 Mid-term Months 19 Last 3 months | Lack of funds for international project coordinator and external consultants. Lack of support or human resources at national level. Lack of support at national level. Lack of support from donors |

Annex 3

Project Implementation Plan (PIP)

For the Implementation of the Component One of the SEE Project Food Legislation

September 2002 – June 2004

| #### Steps | Outputs | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inception and organizational set-up (at both regional and country levels) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Govern ment Commit ment | 1.1 Approval of final project | 1.1.1. Revision and finalization of project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.2 Approval of final draft and annexes by Government r representatives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.3 Endorsement of the decision by the Governments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.4 Presentation of the project to donors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2 Steering Committee & Executive Committee | 1.2.1 Nomination of country representatives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.2.2 SC meetings on progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.2.3 Nomination of members to the EC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.3 Interministerial Bodies At country level | 1.3.1 Nomination of a country project coordinator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.3.2 Establishment of the Interministerial Commission (IMC) and coordinator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.3.3 Approval of Terms of Reference for ICM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| #### Steps | Outputs | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inception and organizational set-up (at both regional and country levels) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Organisa- tional Frame work | 2.1 Implementation infrastructure | 2.1.1 Approval of Terms of Reference for RPM and CPMs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.2 Selection and recruitment of Regional Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.3 Selection and recruitment of CPMs in each country |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.4 Establishment of offices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.5 Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.6 Selection of international consultants on food legislation (both from the region and from EU countries) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2 Work plan and time Table | - Preparation of detailed work plan and timetable for project coordination and implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| #### Steps | Outputs | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IMPLEMENTATION / COMPONENT ONE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. AT REGIONAL LEVEL: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Implementation | 3.A.1 Food and Nutrition Policies and Actions Plans | 3.A.1.1 Provision of international guidance on the process and content of NFNAPS and policies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.1.2 Continuous assistance and review of SEE countries’ NFNAPs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.1.3 1st Technical workshop on FNAPs, cardiovascular diseases and nutrition in the SEE Region, Brijuni, Croatia, September 2002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.1.4 2nd Technical workshop FNAPs, Belgrade, November 2002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.1.5 Pan-European Conference on Nutrition with a satellite meeting of SEE on a new draft project proposal on nutrition, Athens, February 2002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Implementation | 3.A.2 Food Legislation and systems analysis and revision | 3.A.2.1 Elaboration and distribution of questionnaire on Food Legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| #### Steps | Outputs | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IMPLEMENTATION / COMPONENT ONE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. AT REGIONAL LEVEL: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.2.2 Provision of information on the existing food legislative framework in the SEE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.2.3 1st Technical SEE workshop on Nutrition and Food Safety Legislation: Presentation and discussion of the actual legislative situation in the SEE countries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.A.2 Food Legislation and systems analysis and revision | 3.A.2.4 Preparation of detailed Country Reports on the current legislative framework on Food Safety (incl. Gathering intersectorial information, analyzing the situation, proposed updates and reforms) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.2.5 2nd Regional workshop on Food Policy and Legislation in the SEE countries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.A.3 Food Control Systems | 3.A.3.1 Organizing a Regional Forum to discuss development of National Food Safety Strategies, including the basis for establishment of national Food Safety Agencies in the light of EU developments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.3.2 Regional training on investment projects planning and management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| #### Steps | Outputs | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IMPLEMENTATI0N / COMPONENT ONE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.A.4 SEE Regional Food Safety Network | 3.A.4.1 Nomination of responsible national institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.4.2 Establishment of communication lines through email as a start |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.A.4.3 Website |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B. AT NATIONAL LEVEL: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B. Implementation | B.1 National Food and Nutrition Action Plan | B.1.1 Establishing National Task Force |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.1.2 First Draft NFNAP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.1.3 International Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.1.4 Second draft NFNAP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.1.5 Governmental and public consultations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.1.6 Finalization of NFNAPs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.1.7 Adoption |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | B.2 Food Legislation and update | B.2.1 Drafting and/or revision of the primary Food Law |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.2.2 Formulation of National Food Safety Strategy and framework for the development of secondary regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| #### Steps | Outputs | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IMPLEMENTATI0N / COMPONENT ONE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B. AT NATIONAL LEVEL: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementa tion | B.2 Food Legislation and update | B.2.3 Development of codes of practice on the enforcement of the food law |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.2.4 Particular needs from the countries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | B.3 Food Control System Concept | B.3.1 Situation Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.3.2 Analysis of international recommendations and models, particularly in the light of EU developments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.3.3 First draft concept on national food control system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.3.4 Public discussion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B.3.5 Investment project proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | B.4 Capacity building and coaching for implementation | 3.B.4.1 National workshops tailored to the needs of the individual countries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.B.4.2 Provision of international expert consultations upon request |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Annex 4

#### Organizational Set-up

#### for the Food Safety and Nutrition Project

The project organizational set-up comprises of two levels:

At the political level		- a Steering Committee (SC)

At the management level	- an Executive Committee (EC)

- a Regional Project Office (RPO) with a Regional Project Manager  							  (RPM)
						- Country Project Offices (CPOs) with Country Project Managers (CMPs)

Steering Committee (SC)

The key responsibility of the SC is to monitor, supervise and evaluate project implementation. This will be done by approving project reports, i.e. the progress reports and the final report.

- The SC is composed of:

- Representatives from the eight beneficiary countries

- Representative from the WHO Regional Office for Europe

- Representative from the Council of Europe

- Representatives from the donor countries

- The members of the SC are appointed by the Ministers of Health of the participating countries, by the WHO Regional Director and by the CoE Director General for Social Cohesion and Health

- Donor countries without a substantial contribution to the funding of the project can appoint co-opted members to the SC (without vote), provided that the interested countries cover the cost of their participation

- The votes of WHO, CoE and the donor countries constitute the majority in the SC. In particular, their votes are distributed as follows:

- WHO – 1 vote

- CoE – 1 vote

- Italy – 1 vote

- Greece – the rest of the votes

5.	New donor countries will appoint members to the SC at the expense of members appointed by Greece, but in the final constitution of the SC Greece will have a minimum of two votes, as the main partner-donor.

6.	Proposed major changes related to the project sub-components, outputs and activities put forward by an individual country, can be submitted for approval to the SC through the management structure of the project, which also submits its opinion and advice to the SC for its final decision.

7.	The SC amongst its other duties plays the key role of the project promoter and advocate, as well as the role of mobilizer of partners and resources, directed towards the sustainability and successful implementation of the project. In the above context, the SC can propose the transformation of the project, or any of its sub-components, to a long term programme, should additional funds become available through the aforementioned activities of the SC.

- The SC appoints the EC.

- The SC will elect amongst its members, a Chairman and a Rapporteur and will approve the terms of reference for the posts of the RPM and the CPMs.

Executive Committee (EC)

The EC is the highest-level management body of the project.  It, therefore, coordinates and oversees all the project objectives, outputs and activities and supervises the Regional Project Manager, who reports to the EC regularly every two months and in addition whenever it is deemed appropriate.

- The EC is composed of:

- One member from Serbia and Montenegro (project lead country)

- One member from WHO (global advisory organization for health)

- One member from Greece (main partner-donor country)

- The EC is appointed by the SC after nominations by the Ministry of Foreign Affairs of Serbia and Montenegro, the WHO Regional Director for Europe and the Minister of Health and Welfare of Greece

- Once the above nominations have been accepted by the SC, membership of the EC can only change either through resignation of a member or through a decision by the SC

- The EC has the right to re-allocate funds, subject to approval by the members of the donor countries, WHO and CoE.

- The EC has the right to approve extensions from the agreed time frame of implementation, should the situation makes it necessary.

- The EC has the responsibility for resolving crises and disagreements, which occur between individual countries, CPMs, RPM and constitute major deviations from the agreed objectives, outputs and activities of the project.

- The EC introduces for approval to the SC the closure of the budget of the previous year and proposes the budget for the following year

- The proposals of the CPMs and of the RPM with regard to the qualifications and recruitment of the full and part-time salaried staff for the project, has to be approved by the EC prior to their appointment.

- The EC selects the RPM amongst candidates from Serbia and Montenegro (project lead country), through an open and transparent process, in line with the terms of reference approved by the SC in its inaugural meeting, and submits its choice to the government of Serbia and Montenegro for appointment of the successful candidate.

- The EC selects the CPMs from a list of three candidates from each country, proposed by the Ministry of Health, in line with the terms of reference approved by the SC and submits its choice to the respective minister for the appointment of the successful candidate. Interviews of the candidates could be carried out by the EC, should it deem it appropriate.

- The members of the EC decide amongst themselves the chairmanship of the committee, on a rotational basis.

- The EC meets regularly every four months and also at whatever time it deems necessary.

###### Regional Project Manager (RPM)

To secure successful implementation of the project, the RPM has the following duties and responsibilities:

- Coordinates the work of the CPMs

- Responsible for the day-to-day activities of the regional office

- Responsible for the organization and management of the intercountry activities

- Responsible for the monitoring of the progress of project implementation in all participating countries

- Reports every two months to the EC on the progress of project implementation, including problems faced and proposals for solutions, which is based on the country reports

- Reports and proposes subjects for discussion and decision to the EC

- Proposes to the EC re-allocations and changes of outputs and activities, in consultation with the CPMs

- Acts as Secretariat to the EC and the SC

Country Project Manager (CPM):

The CPM is responsible for the successful implementation of the project outputs and activities at the national level. The detailed description of work to be performed by the CPM is defined in the project document. In this context, the CPM has the following main responsibilities, duties and tasks:

- Launches the project in the country

- Prepares the specific sub-objectives, activities, tasks, workplan, timetable and budget (LFA) for the “inception report”

- Prepares the implementation framework for the recipient country

- Organizes the implementation system in the country

- Coordinates the country activities for the project;

- Proposes local experts for hiring under the project as appropriate;

- Liases constantly with the RPM and the national project managers in each of the other recipient countries;

- Mobilizes other relevant governmental institutions, sectors, local authorities and external partners

- Monitors the implementation of activities agreed;

- Reports to the RPM and the EC  in the format required

- Builds up an accounting and invoicing system according to agreed requirements

- Prepares the financial statements and reports to the donors as agreed and submits them through the RPM

- Keeps records and files

Annex 5

Budget Breakdown per SEE Country

For the Implementation of the Component One of the Project on Food Legislation

September 2002 – June 2004

| #### Steps | Outputs |  | Activities |  | Budget Break down by SEE Country in EUROs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Total |  | ALB |  | BIH |  | BUL |  | CRO |  | MDA |  | ROM |  | S&M |  | FYM |  |
| Inception and organizational set-up (at both regional and country levels) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Govern ment Commit ment |  | 1.1 Approval of final project |  | 1.1.1 Revision and finalization of project |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.1.2 Approval of final draft and annexes by Government representatives |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.1.3 Endorsement of the decision by the Governments |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.1.4 Presentation of the project to donors |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.2 Steering Committee & Executive Committee |  | 1.2.1 Nomination of country representatives |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.2.2 SC meetings on progress |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.2.3 Nomination of members to the EC |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.3 Interministerial Bodies At country level |  | 1.3.2 Establishment of the Interministerial Body (IMB) and coordinator |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.3.3 Approval of Terms of Reference for IMB |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Organisa- tional Frame work |  | 2.1 Implementation infrastructure |  | 2.1.1 Approval of Terms of Reference for RPM and CPMs |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 2.1.2 Selection and recruitment of Regional Project Manager |  | 5 715 |  | 715 |  | 715 |  | 715 |  | 7151 |  | 715 |  | 715 |  | 715 |  | 715 |
|  |  |  |  | 2.1.3 Running costs |  | 5 715 |  | 715 |  | 715 |  | 715 |  | 7151 |  | 715 |  | 715 |  | 715 |  | 715 |

| #### Steps | Outputs | Activities | Budget Break down by SEE Country in EUROs |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | ALB | BIH | BUL | CRO | MDA | ROM | S&M | FYM |
| Inception and organizational set-up (at both regional and country levels) |  |  |  |  |  |  |  |  |  |  |  |
| 2. Organisational Framework | 2.1 Implementation infrastructure | 2.1.4 Selection and recruitment of CPMs in each country | 0 |  |  |  |  |  |  |  |  |
|  |  | 2.1.5 Establishment of country offices | 0 |  |  |  |  |  |  |  |  |
|  |  | 2.1.6 Running costs of country offices | 8 000 | 1 000 | 1 000 | 1 000 | 1 000 | 10001 | 1 000 | 1 000 | 1 000 |
|  |  | 2.1.7 Equipment of country offices | 24 000 | 3 000 | 3 000 | 3 000 | 3 000 | 3 0001 | 3 000 | 3 000 | 3 000 |
|  |  | 2.1.8 Selection of international consultants on food legislation (both from the region and from EU countries) |  |  |  |  |  |  |  |  |  |
|  | 2.2 Work plan and time Table | 2.2.1 Preparation of detailed work plan and timetable for project coordination and implementation |  |  |  |  |  |  |  |  |  |

| Steps | Outputs |  | Activities |  | Budget breakdown by SEE Country in EUROs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Total |  | ALB |  | BIH |  | BIL |  | CRO |  | MDA1 | ROM |  |  | S&M |  | FYM |
| IMPLEMENTATION / COMPONENT ONE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. AT REGIONAL LEVEL: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Implementation |  | 3.1 Food and Nutrition Policies and Action Plans |  | 3.1.1 Provision of international guidance on the process and content of NFNAPs and policies |  | -- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 3.1.2 Continuous assistance and review of SEE countries’ NFNAPc |  | -- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 3.1.3 1st Technical Workshop on FNAPs, cardiovascular diseases and nutrition in the SEE region, Brijuni, Croatia, September 2002 |  | 13 751 |  | 1 715 |  | 1 751 |  | 1 751 |  | 1 751 | 1 7501 |  | 1 751 | 1 751 |  | 1 751 |  |
|  |  |  |  | 3.1.4 2nd Technical Workshop on FNAPs, Belgrade, November 2002 |  | 11 428 |  | 1 428 |  | 1 428 |  | 1 428 |  | 1 428 | 1 4281 |  | 1 428 | 1 428 |  | 1 428 |  |
|  |  |  |  | 3.1.5 Pan-European Conference on Nutrition with a satellite meeting of SEE on a new draft project proposal on nutrition, Athens, February 2002 |  | 13 715 |  | 1 715 |  | 1 715 |  | 1 715 |  | 1 715 | 1 7151 |  | 1 715 | 1 715 |  | 1 715 |  |
|  |  | 3.2 Food legislation and systems analysis and revision |  | 3.2.1 Elaboration and distribution of questionnaire on Food Legislation |  | -- |  |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |
|  |  |  |  | 3.2.2 Provision of information on the existing food legislative framework in the SEE |  | -- |  |  |  |  |  |  |  |  | -- |  |  |  |  |  |  |
|  |  |  |  | 3.2.3 1st Technical SEE Workshop on Nutrition and Food Safety Legislation: Presentation and discussion of the actual legislative situation in the SEE countries |  | 11 428 |  | 1 428 |  | 1 428 |  | 1 428 |  | 1 428 | 1 4281 |  | 1 428 | 1 428 |  | 1 428 |  |

| #### Steps | Outputs | Activities | Budget Break down by SEE Country in EUROs |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | ALB | BIH | BUL | CRO | MDA | ROM | S&M | FYM |

| IMPLEMENTATION / COMPONENT ONE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. AT REGIONAL LEVEL: |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.3 Food legislation and systems analysis and revision | 3.3.1 Preparation of detailed Country Reports on the current legislative framework on Food Safety (incl. gathering intersectorial information, analyzing the situation, proposed updates and reforms) | -- | -- | -- | -- | -- | -- | -- | -- | -- |
|  | 3.4 Food legislation revision | 3..4. 2nd Regional Workshop on Food Policy and Legislation in the SEE, Belgrade, May 2003 | 57 142 | 7 142 | 7 142 | 7 142 | 7 142 | 7 1421 | 7 142 | 7 142 | 7 142 |
|  | 3.5 Food Control Systems | 3.5.1 Organizing a Regional Forum to discuss development of National Food Safety Strategies, including the basis for establishment of national Food Safety Agencies in the light of EU developments | 34 285 | 4 285 | 4 285 | 4 285 | 4 285 | 4 2851 | 4 285 | 4 285 | 4 285 |
|  |  | 3.5.2 Regional training on investment projects planning and management | 28 571 | 3 571 | 3 571 | 3 571 | 3 571 | 3 5711 | 3 571 | 3 571 | 3 571 |
|  | 3.6 SEE Regional Food Safety Network | 3.6.1 Nomination of responsible national institutions | 0 |  |  |  |  |  |  |  |  |
|  |  | 3.6.2 Establishing of communication lines through e-mail as a start | 0 |  |  |  |  |  |  |  |  |
|  |  | 3.6.3 Website | 3 428 | 428 | 428 | 428 | 428 | 4281 | 428 | 428 | 428 |
|  |  | 3.6.4 Database and library | 0 |  |  |  |  |  |  |  |  |

| #### Steps | Outputs | Activities | Budget Break down by SEE Country in EUROs |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | ALB | BIH | BUL | CRO | MDA1 | ROM | S&M | FYM |

| IMPLEMENTATION / COMPONENT ONE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B. AT NATIONAL LEVEL: |  |  |  |  |  |  |  |  |  |  |  |
| B.1 Implementation | B.1.1 National Food and Nutrition Action Plan | B.1.1.2 Establishing national Task Force | 127 428 | 15 928 | 15 928 | 15 928 | 15 928 | 15 9281 | 15 928 | 15 928 | 15 928 |
|  |  | B.1.1.3 First draft NFNAP |  |  |  |  |  |  |  |  |  |
|  |  | B.1.1.4 International review |  |  |  |  |  |  |  |  |  |
|  |  | B.1.1.5 Second draft NFNAP |  |  |  |  |  |  |  |  |  |
|  |  | B.1.1.6 Governmental and public consultations |  |  |  |  |  |  |  |  |  |
|  |  | B.1.1.7 Finalization of NFNAPs |  |  |  |  |  |  |  |  |  |
|  |  | B.1.1.8 Adoption |  |  |  |  |  |  |  |  |  |
|  | B.1.2 Food Legislation update | B.1.2.1 Drafting and/or revision of the primary Food Law |  |  |  |  |  |  |  |  |  |
|  |  | B.1.2.2 Formulating of National Food Safety Strategy and framework for the development of secondary regulations |  |  |  |  |  |  |  |  |  |
|  |  | B.1.2.3 Development of codes of practice on the enforcement of the food law |  |  |  |  |  |  |  |  |  |
|  |  | B1.2.4 Particular needs from the countries |  |  |  |  |  |  |  |  |  |
|  | B.1.3 Food Control System Concept | B.1.3.1 Situation Analysis |  |  |  |  |  |  |  |  |  |
|  |  | B.1.3.2 Analysis of international recommendations and models, particularly in the light of EU developments |  |  |  |  |  |  |  |  |  |

| #### Steps | Outputs | Activities | Budget Break down by SEE Country in EUROs |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | ALB | BIH | BUL | CRO | MDA | ROM | S&M | FYM |

| IMPLEMENTATION / COMPONENT ONE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B. AT NATIONAL LEVEL*: |  |  |  |  |  |  |  |  |  |  |  |
| B.1 Implementation | B.1.4 Food Control Systems Concept | B.1.4.1 First draft concept on a national food control system |  |  |  |  |  |  |  |  |  |
|  |  | B.1.4.2 Public discussion |  |  |  |  |  |  |  |  |  |
|  |  | B.1.4.3 Investment project proposals |  |  |  |  |  |  |  |  |  |
|  | B.1.5 Capacity building and coaching for implementation | B.1.5.1National workshops tailored to the needs of the individual countries |  |  |  |  |  |  |  |  |  |
|  |  | B.1.5.2Provision of international expert consultations upon request |  |  |  |  |  |  |  |  |  |
| EVALUATION (At both regional and national levels) |  |  |  |  |  |  |  |  |  |  |  |
| C. 1 Evaluation and Fund raising for follow up | C.1.1 Evaluation of the Implementation | C.1.1.1 Preparation of system and criteria for project reporting, monitoring and evaluation | 0 |  |  |  |  |  |  |  |  |
|  |  | C.1.1.2 Progress and completion report | 0 |  |  |  |  |  |  |  |  |
|  |  | C.1.1.3Evaluation of the update of the primary food laws and of the national situation for development of secondary specific food regulations | 0 |  |  |  |  |  |  |  |  |
|  |  | C.1.1.4 Additional fund raising for capacity building to implement food legislation | 0 |  |  |  |  |  |  |  |  |
| TOTAL FOR COMPONENT ONE, BOTH AT REGIONAL AND NATIONAL LEVELS |  |  | 34 4 570 | 43 070 | 43 070 | 43 070 | 43 070 | 43 0701 | 43 070 | 43 070 | 43 070 |

 To be further specified by each individual country while preparing the country workplan to implement the project within the available funds. Tailoring the activities of the countries to their specific needs is to be made in the frame of the agreed regional outputs.

The office space, furniture, basic equipment, telephone and other communication facilities for Component One will be in kind contribution of each SEE country

Each SEE country will have the opportunity, within the limited allocation, to be provided with some equipment, based on the specific needs, to be used for the project purposes, namely good management and regional communication

The office space, furniture, basic equipment, telephone and other communication facilities for Component One will be in kind contribution of each SEE country

Each SEE country will have the opportunity, within the limited allocation, to provide some equipment based on the specific needs to be used for the project purposes, namely good management and regional communication

The functions described are applicable to a fully developed RPO. At this stage, because of lack of sufficient funds, RPM will be responsible for functions1,3,4,5,6,7 and 8.

Not fully recruited.

Fundraising for activities of MDA in progress.

The office space, furniture, basic equipment, telephone and other communication facilities for Component One will be in kind contribution of each SEE country.

Through the Greek donation.

Each SEE country will have the opportunity, within the limited allocation, to provide some equipment based on the specific needs to be used for the project purposes, namely good management and regional communication.